MHEWS · MULTI-HAZARD EARLY WARNING SYSTEM

# Delivery Status Report

Task-level completion across all 39 specification modules, corrected to separate what’s coded & tested from what’s confirmed running in production.

| 37 / 39 Specs coded & tested | 33 Awaiting deploy or live-fire test | 4 Live & verified | 2 Blocked on partner input |
| --- | --- | --- | --- |

§1  How to read this

The original version of this report collapsed two different questions into one “Complete” label: was the code written and tested, and is it actually running against production right now. Those aren’t the same claim, and for a system that dispatches real emergency alerts, the difference matters. This version scores them separately.

Build status — from each spec’s tasks.md

CODED    every task checked off; unit/integration tests pass

OPEN    one or more tasks still unchecked

Production status — from operational verification, not the spec file

LIVE    migration applied, confirmed working against real traffic

DEPLOY PENDING    migration written, sitting locally — needs a go-ahead to push

UNVERIFIED    deployed, but the one path that matters hasn’t been confirmed firing

BLOCKED    can’t finish without an external party’s answer

§2  Module status

Grouped by the functional module each spec belongs to. Build status reflects tasks.md exactly, one-for-one against the previous report — those numbers were correct. What changed is the second column.

| Module | Specs | Build | Production | Note |
| --- | --- | --- | --- | --- |
| Data Ingestion & Monitoring | 001, 002, 003, 012 | CODED | LIVE | Only module confirmed fully live — no pending migration. |
| Integration & API Gateway | 022, 025 | CODED | DEPLOY PENDING | WhatsApp adapter still mocked in dispatch-alert by design. |
| Impact Analysis (Map Viz) | 008, 023, 034 | CODED | DEPLOY PENDING | impact_analysis_gaps.sql not yet pushed. |
| Administration & Access | 004, 005, 018, 028 | CODED | DEPLOY PENDING | Lockout + access-review migration awaiting push. |
| Alert Authoring / CAP | 006, 014 | CODED | DEPLOY PENDING | CAP v1.2 export migration awaiting push. |
| Dissemination | 009, 015, 021, 027, 031, 036 | CODED | UNVERIFIED | See §3 — dispatch trigger, not just a pending push. |
| Incident Tracking | 011, 026, 033 | CODED | DEPLOY PENDING | Annual incident-report Edge Function awaiting push. |
| Hazard Taxonomy Admin | 010, 016, 020, 024 | CODED | DEPLOY PENDING | Threshold-override migration awaiting push. |
| Audit & Compliance | 007, 019, 029, 030, 035 | CODED | DEPLOY PENDING | audit_compliance_gaps.sql awaiting push. |
| Preparedness, Drill & Response | 013, 017, 032, 037 | CODED | DEPLOY PENDING | Annual drill-report Edge Function awaiting push. |
| Population Exposure Sources | 038 | OPEN · 35/36 | BLOCKED | Live HDX dataset-resolution match for Turkey, not a code change. |
| Risk & Scenario Modeling | 039 | OPEN · 38/39 | BLOCKED | Waiting on UNDP's answer on the INFORM feed's resolution. |

§3  Known verification gap

DISSEMINATION · AUTOMATED CAP DISPATCH The one thing “Complete” cannot mean here: confirmed sending real alerts. The notify_dispatch_on_broadcast() trigger that fires an email dispatch the instant a CAP alert goes to broadcast depends on a service_role_key read from Supabase Vault at runtime. That key was found misconfigured once already and corrected — but the Edge Function’s own environment value still doesn’t demonstrably match the current valid key, and this has not been confirmed working end-to-end against a real broadcast. Practically: every other line item in the Dissemination row is genuinely built and unit-tested — contacts, retries, unsubscribe, region targeting, shelter display. This one specific path (silent automated email dispatch on broadcast) needs a live-fire test before anyone treats it as operational.

§4  What this means for the partner message

The underlying work checks out — every spec’s tasks are genuinely done, tested, and traceable to a real migration file. The only correction needed is in how “done” gets communicated externally.

SUGGESTED REFRAME Every module in scope has been spec’d, built, and tested — 37 of 39 modules are fully coded, with the remaining two blocked purely on your input, not ours. Live-production verification is still pending on a specific set of items: most are simply a deploy-approval step away, and one (automated CAP dispatch email) needs a real-world test before we call it operational. We’d rather flag that now than after a real alert goes out.